## Sheet 1
Task | Estimated Time to Complete(h) | Real Time to Complete (h) | Raffi | Duncan | Matthew B. | Ethan | Omer | Date of Team Meating
1.1 Overview | 1 | 1 | -1
1.2 SDLC | 1 | 1 | -1
1.3 WBS | 4 | ??
1.4 Gantt Chart | ?? | ??
2.1.1 Group Meeting | 0.5 | 0.5 | -0.06 | -0.06 | -0.06 | -0.06 | -0.06
2.1.2 Do Tasks (With Testing) | Total Estimated Time | Total Time
Task 1) Build Prototype | 5 | 4 |  | (2) | (2)
Task 2) Enter Task Name Here
Task 3) Enter Task Name Here
2.1.4 Usability
2.2.1 Group Meeting | 0.5 | 0.5 |  | -0.125 | -0.125 | -0.125 | -0.125
2.2.2 Do Tasks (With Testing) | ?? | ??
Task 1) Enter Task Name Here | 5 | 4
Task 2) Enter Task Name Here
Task 3) Enter Task Name Here
2.2.4 Usability
2.3.1 Group Meeting | 0.5 | 0.5 |  | -0.125 | -0.125 | -0.125 | -0.125
2.3.2 Do Tasks (With Testing) | ?? | ??
Task 1) Enter Task Name Here | 5 | 4
Task 2) Enter Task Name Here
Task 3) Enter Task Name Here
2.3.4 Usability